## WAMI-PP MADZHAROVO
WAMI |  | P3 (Municipality of Madzharovo) Procurement Plan
4. External expertise and Services |  |  |  | Procedure | Tender Date
Insert WP | Insert Action | Insert Expertise or Service Category | Brief Description of the Service (type, purpose, quantities, etc) (Max 300 Characters) | Procedure | Tender Date
WP1 | 1.1 | Technical and scientific Expertise | Preparation activities - Project proposal preparation contract - Madzharovo | Contracted trough public procurement | 19/10/2010 FA
WP1 | 1.2 | Other (please specify) | Project management for MoM - organisation and management, coordination of the activities, financial management and monitoring, technical and financial reporting | Contracted trough public procurement | 19/10/2010 FA
WP1 |  | Technical and scientific Expertise | Project audit - Bulgarian auditor | Direct Award | may 2013
WP2 | 2.1 | Event organisation | Press conferences for the start and the closure of the project | Direct Award | august 2012
WP2 | 2.1 | Event organisation | Official opening of the reconstructed site in MoM
WP2 | 2.2 | Communication/Dissemination material | Publications in national and regional newspapers Bg
WP2 | 2.3 | Other (please specify) | Project sign boards BG
WP2 | 2.3 | Other (please specify) | Project sign constantly information plate, BG
WP3 | 3.3 | Works | Waste water treatement measures in MoM | Open Tender | september 2012
| 3.3 | Supervision of construction works | Designers supervision - Madzharovo | Direct Award | september 2012
| 3.3 | Supervision of construction works | Construction supervison - Madzharovo | Direct Award | september 2012
| 3.3 | Technical and scientific Expertise | Preparation of sub-tendering procurement documentation for MoM - service contract | Contracted trough public procurement | 19/10/2010 FA
WP4 | 4.3 | Event organisation | hall and equipment | Direct Award | September 2012
| 4.3 | Event organisation | lecturers for Seminar 2"Drinking and waste water treatment inovative technologies"
WP4 | 4.3 | Event organisation | materials for Seminar 2"Drinking and waste water treatment inovative technologies"
WP4 | 4.3 | Event organisation | organisation costs for Seminar 2"Drinking and waste water treatment inovative technologies"
WP4 | 4.3 | Event organisation | coffe breaks and refreshments
WP4 | 4.3 | Event organisation | travel
WP4 | 4.3 | Event organisation | 1 lunches and 1 dinners for the participants
WP4 | 4.3 | Event organisation | accomodation
WP5 | 4.3 | Communication/Dissemination material | Brochure "Drinking and waste water treatment - by yourself"
WP5 | 5.4 | Translations/Interpreters | Services related to translations for events and publications - per sheet | Direct Award | September 2012
WP5 | 5.4 | Translations/Interpreters | Services related to translations for events and publications - per hour